## Project X
| Period 1 | Period 2 | Period 3 | Period 4 | Period 5 | Period 6
Planned Value (PV) | 10000 | 25000 | 15000 | 10000 | 25000 | 15000
Cumulative Planned Value (PV) | 10000 | 35000 | 50000 | 60000 | 85000 | 100000
Actual Cost (AC) | 10000 | 26000 | 18000 | 12000 | 29000 | 17000
Cumulative Actual Cost (AC) | 10000 | 36000 | 54000 | 66000 | 95000 | 112000
% Actual Work Complete | 8% | 24% | 32.5% | 37.5% | 54% | 62.5%
% Planned Work Complete | 6% | 20.5% | 29.5% | 35% | 50% | 59%
Rate of Performance (RP) | 1.3333 | 1.1707 | 1.1017 | 1.0714 | 1.08 | 1.0593
Earned Value (EV) = PV*RP | 13333.3333 | 40975.6098 | 55084.7458 | 64285.7143 | 91800 | 105932.2034
Cost Variance (CV) = EV-AC | 3333.3333 | 4975.6098 | 1084.7458 | -1714.2857 | -3200 | -6067.7966
Schedule Variance (SV) = EV-PV | 3333.3333 | 5975.6098 | 5084.7458 | 4285.7143 | 6800 | 5932.2034
Cost Perf Indicator (CPI) = EV/AC | 1.3333 | 1.1382 | 1.0201 | 0.97403 | 0.96632 | 0.94582
Schedule Perf Ind (SPI) = EV/PV | 1.3333 | 1.1707 | 1.1017 | 1.0714 | 1.08 | 1.0593
Estimate at Completion (EAC) | 127500 | 149357.1429 | 166652.3077 | 174533.3333 | 175925.9259 | 179737.6
Estimated Time to Complete (ETC) | 7.5 | 8.5417 | 9.0769 | 9.3333 | 9.2593 | 9.44
Budget at completion (BAC) | 170000
Remaining work | 64067.7966
Remaining funds | 67737.6
To-complete performance index (TCPI) | 0.94582
Conlusion: | For the first 3 period, project X was under budget but became over budget for period 4, 5, 6. However, project X did well in being ahead of schedule for the first 6 period. At the end of period 6, project X has a CPI=0.946, which means it is now over budget and a SPI=1.059, which means it is now ahead of schedule. The estimate at completion cost $179,738 and the estimated time to complete is 9.44 weeks. And we can continue with a Cost Performance Index of 0.95 to complete the project.

## Project Y
| Period 1 | Period 2 | Period 3 | Period 4 | Period 5 | Period 6
Planned Value (PV) | 10000 | 25000 | 15000 | 10000 | 25000 | 15000
Cumulative Planned Value (PV) | 10000 | 35000 | 50000 | 60000 | 85000 | 100000
Actual Cost (AC) | 10000 | 26000 | 18000 | 12000 | 29000 | 17000
Cumulative Actual Cost (AC) | 10000 | 36000 | 54000 | 66000 | 95000 | 112000
% Actual Work Complete | 4% | 17.5% | 25% | 31% | 46% | 55%
% Planned Work Complete | 6% | 20.5% | 29.5% | 35% | 50% | 59%
Rate of Performance (RP) | 0.66667 | 0.85366 | 0.84746 | 0.88571 | 0.92 | 0.9322
Earned Value (EV) = PV*RP | 6666.6667 | 29878.0488 | 42372.8814 | 53142.8571 | 78200 | 93220.339
Cost Variance (CV) = EV-AC | -3333.3333 | -6121.9512 | -11627.1186 | -12857.1429 | -16800 | -18779.661
Schedule Variance (SV) = EV-PV | -3333.3333 | -5121.9512 | -7627.1186 | -6857.1429 | -6800 | -6779.661
Cost Perf Indicator (CPI) = EV/AC | 0.66667 | 0.82995 | 0.78468 | 0.80519 | 0.82316 | 0.83232
Schedule Perf Ind (SPI) = EV/PV | 0.66667 | 0.85366 | 0.84746 | 0.88571 | 0.92 | 0.9322
Estimate at Completion (EAC) | 255000 | 204832.6531 | 216648 | 211129.0323 | 206521.7391 | 204247.2727
Estimated Time to Complete (ETC) | 15 | 11.7143 | 11.8 | 11.2903 | 10.8696 | 10.7273
Budget at completion (BAC) | 170000
Remaining work | 76779.661
Remaining funds | 92247.2727
To-complete performance index (TCPI) | 0.83232
Conlusion: | Project Y went over budget and was behind schedule for the first 6 periods. However, we could see project Y has been improving in scheduling and it's SPI has been increasing. At the end of period 6, project X has a CPI=0.832, which means it is now over budget and a SPI=0.932, which means it is now still behind schedule. The estimate at completion cost $204,247 and the estimated time to complete is 10.73 weeks. And we can continue with a Cost Performance Index of 0.83 to complete the project.

## Project Z
| Period 1 | Period 2 | Period 3 | Period 4 | Period 5 | Period 6
Planned Value (PV) | 10000 | 25000 | 15000 | 10000 | 25000 | 15000
Cumulative Planned Value (PV) | 10000 | 35000 | 50000 | 60000 | 85000 | 100000
Actual Cost (AC) | 8000 | 17500 | 9000 | 14000 | 20500 | 11500
Cumulative Actual Cost (AC) | 8000 | 25500 | 34500 | 48500 | 69000 | 80500
% Actual Work Complete | 4% | 17.5% | 25% | 31% | 46% | 55%
% Planned Work Complete | 6% | 20.5% | 29.5% | 35% | 50% | 59%
Rate of Performance (RP) | 0.66667 | 0.85366 | 0.84746 | 0.88571 | 0.92 | 0.9322
Earned Value (EV) = PV*RP | 6666.6667 | 29878.0488 | 42372.8814 | 53142.8571 | 78200 | 93220.339
Cost Variance (CV) = EV-AC | -1333.3333 | 4378.0488 | 7872.8814 | 4642.8571 | 9200 | 12720.339
Schedule Variance (SV) = EV-PV | -3333.3333 | -5121.9512 | -7627.1186 | -6857.1429 | -6800 | -6779.661
Cost Perf Indicator (CPI) = EV/AC | 0.83333 | 1.1717 | 1.2282 | 1.0957 | 1.1333 | 1.158
Schedule Perf Ind (SPI) = EV/PV | 0.66667 | 0.85366 | 0.84746 | 0.88571 | 0.92 | 0.9322
Estimate at Completion (EAC) | 204000 | 145089.7959 | 138414 | 155147.8495 | 150000 | 146802.7273
Estimated Time to Complete (ETC) | 15 | 11.7143 | 11.8 | 11.2903 | 10.8696 | 10.7273
Budget at completion (BAC) | 170000
Remaining work | 76779.661
Remaining funds | 89500
To-complete performance index (TCPI) | 0.85787
Conlusion: | Project Z went over budget in the first week but was managed to stay under budget from week 2 to week 6. However, project Z has been behind schedule for the first 6 weeks. At the end of period 6, project X has a CPI=1.158, which means it is now under budget and a SPI=0.932, which means it is now still behind schedule. The estimate at completion cost $146,803 and the estimated time to complete is 10.73 weeks. And we can continue with a Cost Performance Index of 0.86 to complete the project.